## Project Info
CSIS 2430 — Project Two Plan
1) Project Information
Course / Term | CSIS 2430
Project | Project 2
Team Name | Team Awesome Sauce
Start Date | 2026-03-09
Due Date | 2026-03-22
Checkpoint Date (mid-project) | 2026-03-15
2) Team & Roles (assigned for this project)
Roles are assigned per project and rotate between projects.
Team Member | Role (Implementation / Verification / Communications) | Primary Responsibilities (1–2 bullets) | Availability / Notes
Benjamin Paul | Implementation Lead | Owns core algorithm implementation; integrates modules; maintains main branch health. | Every night after 5pm most weekday nights
Nelson Long | Verification Lead | Creates test plan; edge cases; validates outputs; documents verification evidence.
Noah Kolling | Communications Lead | Assembles report/video; ensures run instructions; tracks deliverables; merges documentation.
3) Repository & Access (Required for Projects 1–4)
Platform | GitHub
Repository URL | https://github.com/Ben1078/CS-2430-Project-2
Instructor invited as viewer by checkpoint? | Yes — invited 2026-03-18
Repo Structure Requirement (summary) | ReadMe, /DOCS (Project Plan, Pseudo, Scope Document), /src (project2.java, project2Test.java)
Task Tracking (Trello) | https://trello.com/b/IEhcBGHM/2430-project-2

## Milestones
4) Milestones (Timeline)
Define 4–6 milestones. Each milestone has a definition of done. Status: NS / IP / D.
Milestone | Target Date | Owner | Definition of Done | Status (NS/IP/D) | Evidence Link / Pointer
Repo set up + skeleton running | 2026-03-18 | Nelson | Repo created; README run steps; sample I/O runs. | D
Core implementation complete | 2026-03-20 | Ben | All required features implemented; compiles/runs end-to-end. | IP
Verification complete | 2026-03-21 | Nelson | Test suite covers edge cases; expected vs actual documented. | NS
Report/video draft complete | 2026-03-22 | Noah | Draft report sections complete; video outline + script notes. | NS
Final integration + submission | 2026-03-22 | Noah | All deliverables finalized; tags release; submission package ready. | NS

## Tasks
Trello
Issue key | Summary | Status | Due date | Assignee | Updated | Description
P2-1 | Pseudocode | To Do | 3/18 | Benjamin Paul | 22/Feb/26 8:41 PM
P2-2 | Scope Document | To Do | 3/18 | Nelson Long | 22/Feb/26 6:49 PM
P2-3 | Project Plan | To Do | 3/18 | Noah Kolling | 23/Feb/26 3:48 AM
P2-4 | Implement Sorting Algorithms | To Do | 3/20 | Benjamin Paul | 23/Feb/26 3:28 AM
P2-5 | Video Script | To Do | 3/21 | Noah Kolling | 23/Feb/26 3:47 AM
P2-6 | Start Team Report | To Do | 3/21 | Nelson Long | 22/Feb/26 6:40 PM
P2-7 | Unit Tests | To Do | 3/21 | Nelson Long | 22/Feb/26 6:40 PM
P2-8 | Video Recordings | To Do | 3/21 | ALL | 23/Feb/26 4:07 AM
P2-9 | Video Editing | To Do | 3/22 | Noah Kolling | 23/Feb/26 4:07 AM
P2-10 | Final Submission | To Do | 3/22 | Noah Kolling | 23/Feb/26 3:28 AM

## Verification Plan
6) Verification Plan
This projects completeness will be determined by the code’s ability to pass the JUnit tests implemented by Nelson
Additional tests will also be done in main

## Risks
7) Risks / Blockers
Risk / Blocker | Impact | Mitigation Plan | Owner | Status
Communication | LOW | Quickly respond to messages and monitor discord | ALL | Ongoing

## Updates
8) Update Log (Required: at least 2 per project)
Date | Summary of Update (what changed / what completed) | Blockers / Resolutions | Link(s)
2026-03-17 | First Meeting held and a plan was discussed | Miscommunications
2026-03-17 | Github created and started, pseudocode finished | None | https://github.com/Ben1078/CS-2430-Project-2
2026-03-17 | Trello Board Created | None | https://trello.com/b/IEhcBGHM/2430-project-2